## Bidder Instructions
1 | Enter Company Name in Row 3
2 | Enter Number of Events and Cost Per Event for each Milestone Listed under Base Scope of Work/Bid/Contract Price
3 | Confirm Total for Each Milestone Row is correct
4 | Confirm Total Base Contract Price is correct
5 | Enter Cost Per Event, Unit Cost, or Cost Adder for each Optional Milestone listed under Optional Milestones/Cost Adders/Unit Costs
6 | Confirm one more time that all costs are provided and calculations are correct
7 | An authorized representative of the company must sign the Bid Cost Submission Form in Row 4; include typed name and title
8 | Ensure proper formatting for .pdf and electronic bid submission versions; please confirm all milestones, costs, totals rows and columns are visible in your submission
9 | Final review to ensure complete and all information is legible

## Bid Cost Submission Form
Bid Cost Submission Form Request for Bid for Mill Creek Sunoco PADEP Facility ID# 09-43609 PAUSTIF Claim #20230041(I)
The bidder shall provide its bid cost only in the Bid Cost Submission Form with descriptions for each task provided in the body of the bid document. No cost information should be provided in the technical submittal. Bidders are responsible to ensure all costs are provided in the Bid Cost Submission Form, and calculations (including, but not limited to the total bid cost) are accurate; the Bid Cost Submission Form must be signed by an authorized representative of the company. In addition, bidders are required to include, as backup for the Bid Cost Submission Form, a list of bid labor rates and a detailed breakdown of each milestone fixed-cost including, but not limited to, labor, subcontractor costs and mark-up, direct costs, and equipment. The technical score for bids will be based solely on those tasks represented as milestones included in the Bid Cost Submission Form and the total bid cost. Any optional bidder-defined tasks, milestones, or cost adders that are not requested as part of this RFB will not be considered by the Bid Evaluation Committee in the technical review and technical score for the bid.
Submitted by: [Insert Bidder Company Name]
Signature of Authorized Company Representative: Typed Name: Title: Date:
Base Scope of Work/Bid/Contract Price
Milestone | Description | Number of Events | Cost Per Event | Total Cost
A | Obtain Property Access | 1 |  | 0
B | Separate Phase Liquid Assessment | 1 |  | 0
C | Private Utility Mark-out | 1 |  | 0
D | Soil Boring Installation and Sampling | 1 |  | 0
E | Monitoring Well Installations | 1 |  | 0
F | Vapor/Soil Gas Sample Point Abandonments and Installations | 1 |  | 0
G | Professional Survey | 1 |  | 0
H | Groundwater Monitoring and Sampling | 2 |  | 0
I | Sub-Slab Soil Gas Sampling | 2 |  | 0
J | Site Characterization Report | 1 |  | 0
|  | Total Base Contract Price |  | 0
Optional Milestones/Cost Adders/Unit Costs
Optional Milestone | Description | Cost Per Event/ Unit Cost | Unit
K | Obtain PennDOT Access |  | Per Event
L1 | Install one additional soil boring as a stand-alone (include mob costs) |  | Per Soil Boring
L2 | Install one additional soil boring as an add-on (do not include mob cost) |  | Per Soil Boring
L3 | Cost Adder/Reducer Per-foot cost to modify the reimbursement for the installation of a soil boring |  | Per Foot
M | Cost Adder/Reducer to Collect Additional or Fewer Soil Sample(s) |  | Per Sample
N | Cost Adder/Reducer to Collect Additional or Fewer Geotechnical Sample(s) |  | Per Sample
O1 | Install off-property monitoring wells MW-16, MW-17, and MW-18. |  | Per Event
O2 | Install on-property monitoring wells MW-19, MW-20, and MW 21. |  | Per Event
P1 | Install one additional monitoring well as a stand-alone (include mob cost) |  | Per Well
P2 | Install one additional monitoring well as an add-on (do not include mob cost) |  | Per Well
P3 | Cost Adder/Reducer Per-foot cost to modify the reimbursement for the installation of a monitoring well |  | Per Foot
Q1 | Update survey to include off-property monitoring wells MW-16, MW-17, and MW-18 installed as Optional Milestone O1 as a stand-alone (include mob cost) |  | Per Event
Q2 | Update survey to include on-property monitoring wells MW-19, MW-20, and MW-21 installed as Optional Milestone O2 as a stand-alone (Include mob cost) |  | Per Event
Q3 | Update survey to include one additional soil boring (do not include mob cost) |  | Per Soil Boring
Q4 | Update survey to include one additional monitoring well (do not include mob cost) |  | Per Well
Q5 | Update survey to include monitoring wells MW-2, MW-3, and MW-4 and injection wells IW-1, IW-4, and IW-5 at the former CITGO station property as a stand-alone (Include mob cost) |  | Per Event
R1 | Complete one round of water level measurements from monitoring locations MW-8 through MW-21, OB-1, and the sump as a stand-alone (include mob cost) |  | Per Event
R2 | Complete one round of water level measurements from monitoring locations MW-8 through MW-21, OB-1, and the sump and one groundwater sampling event from monitoring wells MW-8 through MW-21 as a stand-alone (Include mob cost) |  | Per Event
R3 | Cost Adder/Reducer Complete water level measurement and groundwater sampling of one monitoring well as an add-on |  | Per Well
R4 | Cost Adder/Reducer Complete SPL measurement, and removal, weighing, and replacement of one absorbent sock at one well |  | Per Well
R5 | Cost Adder/Reducer Collect an additional or less 0.5-gallons of SPL to be containerized and disposed. |  | Per 0.5-gallon
S1 | Perform a SPL recoverability assessment at one additional well over the course of six events. (Do not include mob costs) |  | Per Well
S2 | Cost adder/Reducer Perform one SPL measurement and recovery event at one well. |  | Per Well
T1 | Complete VI sampling event as an add-on (do not include mob cost) |  | Per Event
T2 | Complete VI sampling event as a stand-alone (include mob cost |  | Per Event
T3 | Cost Adder/Reducer Complete VI sampling at one sub-slab soil gas sampling point (do not include mob) |  | Per Sampling Point
U1 | Minor monitoring well repair as an add-on (do not include mob cost) |  | Per Well
U2 | Major monitoring well repair as an add-on (do not include mob cost) |  | Per Well
U3 | Major monitoring well repair as a stand-alone event (include mob cost) |  | Per Well
V | Install and Sample additional Sub-Slab Vapor/Soil Gas Sampling Points |  | Per Event