## Base SOW - Cost Table
Bid Cost Spreadsheet
Honey Bear Mini Mart, Kittanning, PA, Claim #2002-0197(I)
Competitive Bid Solicitation for Remediation To Closure Via Statewide Health Standard
[Insert Bidder Company Name Here]
COST COMPONENT |  | Milestone A Supplemental Site Characterization Activities and Reporting | Milestone B Pilot Testing and Reporting | Milestone C Documentation of Findings: RAP Addendum or Revised RAP | Milestone D Pre-Remediation Quarterly Groundwater Monitoring, Sampling & Reporting (Qtly Fixed Price Unit Costs) | Milestone E - RAP Implementation | [5 empty] | Milestone F Remedial System O&M and Groundwater Monitoring, Sampling & Reporting (Qtly Fixed Price Unit Costs) | Milestone G Soil Attainment Demonstration | Milestone H Groundwater Attainment Demonstration (Qtly Fixed Price Unit Costs) | Milestone I Follow-up Vapor Instusion Study | Milestone J Preparation, Submittal and PADEP Approval of Remedial Action Completion Report (RACR) | Milestone K Site Closure / Restoration Activities | Base SOW Subtotal | Optional Cost Adder Milestone D3 through Dn Additional Pre-Remediation Quarterly Groundwater Monitoring, Sampling & Reporting (Qtly Fixed Price Unit Costs) | Optional Cost Adder Milestone F13 through Fn Additional Remediation System O&M and Groundwater Monitoring, Sampling & Reporting (Qtly Fixed Price Unit Costs) | Optional Cost Adder Milestone H9 through H12 Additional Groundwater Attainment Demonstration (Qtly Fixed Price Unit Costs) | Optional Cost Adder Milestone UC1 Additional Monthly Operation of CatOx Unit (Monthly Fixed Unit Price Costs) | Optional Cost Adder Milestone UC2 LGAC Change -Out | Optional Cost Adder Milestone UC3 VGAC Change-Out
[6 empty] | MilestoneE1 Installation of Remediation System Wells | Milestone E2 In-Situ Remedial System Final Design, Equipment Purchase, and Assembly | Milestone E3 Site Preparation Work | Milestone E4 In-Situ Remediation Equipment Pad, Trenching, Subsurface Piping, Mechanical, and Electrical | Milestone E5 Final Connections and Startup / Trouble-Shooting of the In-Situ Remediation System | Milestone E6 Temporary Operation of a CatOx Unit and Initial Setup of VGAC Units (Monthly Fixed Unit Price Costs)
Associated Milestone |  | A | B | C | D | E1 | E2 | E3 | E4 | E5 | E6 | F | G | H | I | J | K | 0 | D3 through Dn | F13 through Fn | H9 through H12 | UC1 | UC2 | UC3
Anticipated # of Milestone Payments |  | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 6 | 12 | 1 | 8 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Labor | Bidders shall enter costs for each labor/ODC/Sub category based on the proposed payment for achieving each milestone. The total cost for completion of each Task will be the "Subtotal" multiplied by the "Anticipated # of Milestone Payments" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs1 | [12 empty] | 0 |  |  |  |  | 0
ODC ≥$5,000 (Specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC ≥$5,000 (Specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ODC ≥$5,000 (Specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other ODCs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontracted Costs2 | [17 empty] | 0
Analytical Laboratory - Water |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analytical Laboratory - Soil |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analytical Laboratory - Vapor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Analytical |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equipment Rental |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Geoprobe / Driller |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Waste Disposal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Professional Surveyor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Excavation Contractor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electrical Contractor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other (specify) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Per Milestone Subtotal |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 10000 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
Schedule of Unit Labor Rates | HOURLY RATE |  |  |  |  | Milestone D - Irrespective of the two quarters indicated above, all bidders shall indicate below the total/cumulative number of quarterly monitoring & reporting events that are expected to be needed before implementation of the remedial approach. | [5 empty] | Milestone F - All bidders shall indicate below the additional number of system O&M quarters (beyond the 12 quarters indicated above for Milestone F) that are expected to be needed for the Site to reach SHS for all COC's in groundwater & soil under the bidders care.
Sr. Project Engineer, P.E. | 0 |  |  |  |  | Quarterly Events Prior to RAP Implementation >>> | [5 empty] | Additional Quarters of Remedial System O&M >>>
Project Geologist/ Engineer | 0
Associate Project Geologist/ Engineer | 0
Staff Geologist/ Engineer | 0
Sr. Field Technician | 0
Field Technician | 0
Word Processor | 0
Draftsman | 0
Project Coordinator | 0
Junior Professional | 0
Other (specify) | 0
Other (specify) | 0
Other (specify) | 0
Other (specify) | 0
Subcontractor / Vendor Mark-up (%) | %
1 - Individual other direct cost line items totaling $5,000 or more must be specified (use separate sheet, if necessary).
2 - Details related to subcontracted costs are requested by the Solicitor to assist in the evaluation of the costs associated with the performance of this work.
3 - Bidders shall only enter data into Bid Form areas (Excel file cells) that are shaded in blue.